## Release Plan
Project Management - Release Plan
Release | Features | Estimated Timeline
Sprint 0 | • Constant communication with the proposed client and conducting further user research is performed by the project team to effectively understand the need, the MVP and the basic components required to add to the system. • The project team systemize and are assigned roles and responsibilities to compose all the relevant documentation used to plan out the desired outcomes that will be achieved throughout the product completion process, including; the recording of user stories (desired tasks) that each user would request that the system should provide, the recording of SCRUM meeting discussions amongst project team members to review the current objectives and future goals in completing the product, designing and implementing the various back-end design diagrams to effectively identify the flow of logic that the system will possess to achieve the desired outcome of the system, etc. | 14 April - 9th June Definition of Done: Requirements reviewed by product owner, criteria for acceptance were satisfied. non-functional needs were met, user stories is approved by the product owner. Target date for release: 22 May
Sprint 1 | • The streamlining of the documentation provided in the previous Sprint as the project team consistently develop the system during the desired timeline. • The commencing of the project team providing the hard-coding development of the project by the project team analyzing any coding tasks that was stated in the documentation, such as; Authentication. | 4 August - 8 September Definition of Done: All user stories that is part of the sprint has its DoD met, all unit tests have been passed., the updating of Sprint 1 documents such as the product backlog. Project launched on a platform that is identical to the production environment in testing, device/browser tests on those indicated in the manual were successful, backward compatibility tests were successful, performance testing were successful, no bugs were detected during coding process. The Product Owner marked the sprint as prepared for production deployment. Target date for release: 25 August
Sprint 2 | • The final Sprint of the project development process which comprises of the final deployment of the project system, the adjornment of the project team which will allow each team member to conduct evaluations of performance throughout the Project Development Lifecycle, and a final demonstration presentation that will be done to the client to submit and show the final solution of the project in its entirety. | 9 September - 20 October Definition of Done: Software code is compiled and completed, testing environments are prepared for release, All functional and unit tests have passed, all the acceptance criteria are met. All issues were found and fixed during quality assurance. OK from the team: QA, project manager, software architect, UX designer, developer, etc. Verify that no staging or development environment has any unfinished work still in progress. Target date for release: 9 October
Release 1: MVP | • User Authentication is acquired. • User profile with designated dashboard viewed based on user-credentials. • Ticket creation form is accessible. • Technican page is visibile to provide direct response to user generated queries. | 4 August - 8 September
Release 2: Student Dashboard | • List of generated tickets generated by students with status of completion. • Student notification through email that ticket was created using the system. • Contact page to allow students to contact technicans for further assistance regarding queries submitted on the system. | 4 August - 8 September
Release 3: Technican Dashboard | • Technicans can create and view response templates for quick and "easy-fix" solutions situated on their dashboard. • Priority of concern can be adjusted and implemented to student queries based on ticket severity. • The systems will notify technicans if tickets are not responded at the appropriate time. | 9 September - 20 October
Release 4: Reporting | • Technicans can generate reports to record each query submitted by a specified provides consolidated, factual and an up-to-date information which will be well organized and can be used for future planning and decision making of ticket response procedures. • Students can modify established tickets by deleting previous tickets or cancel any new tickets upon creation in the case of errors. | 9 September - 20 October
Release 5: Website | • Website generated using MVC .net Core Web application using Visual Studio 2022 in C# coding language. • Published access for outside use and to not rely on locally executed application. • Careful and concise checking across each project team member to validate if the user acceptance criteria stated by the project owner and the client was met and the basic functionality is present in the application. • Hard-coded application undergoing various testing to ensure effective release and production of final solution to be submitted to the client for future use. • Controlled, live demonstration of final solution to the client for review. | 4 August - 20 October

## Product Backlog
Story ID | User Stories/Description | Story Type | Acceptance Criteria | Sprint No | Backlog Priotity | Estimated Effort | Sprint Start Date | Sprint End Date
PB001 | As a project team member, I want to conduct online research to investigate authentication and signing in to the website during the Sprint Planning process. | Technical Story Spikes | Investigating the effect of two-factor verification that assists students to access their accounts more securely, especially while viewing sensitive information and provides an additional security step that helps protect student accounts by making it harder for other people to break in, this includes; allocating a prompt for a second verification method after you sign in with your studentname and password and issuing a sign-in without requiring a password, using your username and your mobile device with your fingerprint, face, or PIN. | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 2 | 2023-04-14 | 2023-06-09
PB002 | As a project team member, I want to create a prioritized Product Backlog with a list of features and user stories during the Sprint Planning Meeting so that we can plan and prioritize our work effectively and proceed with responding to user stories from the product backlog. | Technical Story Spikes | A categorized, scheduled project timetable that will thoroughly indicate the relevant deliverables (such as new features) will be implemented as part of the project development process and it will be used as a decision-making artifact will assist with estimating, refining, and prioritizing everything the project team may use for future projects. As well as the definition of the project scope, goals, and objectives will be identified during the Sprint Planning Meeting so that everyone is aligned on what needs to be accomplished. | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 5 | 2023-04-14 | 2023-06-09
PB003 | As a project team member, I want to conduct student research and gather requirements during the Requirement Analysis phase so that we have a clear understanding of the users' needs and expectations. | Technical Story Spikes | This will be achieved by the project manager who will ensure that the plan of action aligns with their stakeholders' needs. This can be achieved through brainstorming, the project team will consider different parts of the system individually by exploring various what-if scenarios and blue-sky ideas as the outcome of the sessions is to break away from existing conventions. Consider different ideas for pushing current boundaries. Using useful tools for brainstorming sessions include whiteboards, mind mapping software, and empathy maps (the latter for exploring student needs). | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 3 | 2023-04-14 | 2023-06-09
PB004 | As a project team member, I want to create user personas and user stories during the Requirement Analysis phase to better understand our target audience and their specific requirements. | Technical Story Spikes | During the Requirement Analysis phase, the transforming of student needs and high-level requirements specified in earlier phases will be assessed through measureable, traceable, complete, consistent, and stakeholder-approved requirements. This will be acheieved through user cases and interviews as user cases walk stakeholders through the development, and use of, a product ocassionally featuring a prototype of the future product). Interviews help project teams gather data regarding stakeholder requirements for a project. | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 3 | 2023-04-14 | 2023-06-09
PB005 | As a project team member, I want to develop a UI/UX design that meets user requirements during the Design phase to ensure an intuitive and user-friendly website will be implemented. | Technical Story Spikes | UI/UX design is one among numerous non-technical roles in tech that doesn’t require any coding or programming skills. However, having previous experience in coding or programming skills is beneficial as communicating with developers is made easier, as well as it improves the user experience and customer satisfaction that ultimately helps increase the number of users of the specific application. And to analyze the target audience and their needs, to research, create an efficient layout and well-thought-out system of transitions, wrap it in an attractive but highly usable and clear visual design, and test the solutions. | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 5 | 2023-04-14 | 2023-06-09
PB006 | As a project team member, I want to create a UML Use Case Diagram to visualize the system's functionality during the Design phase so that we have a clear understanding of how different components interact with each other. | Technical Story Spikes | Class diagrams are the only diagrams which can be directly mapped with object-oriented languages and thus widely used at the time of construction. UML diagrams like activity diagram, sequence diagram can only give the sequence flow of the application, however class diagram is a bit different as they are graphical representation of the static view of the system and represents different aspects of the application. A collection of class diagrams represent the whole system. The method of developing a class diagram is as follows: The name (such as Technical Support System) should be meaningful to describe the aspect of the system. Each element and their relationships should be identified in advance. The Responsibility (attributes and methods) of each class should be clearly identified. For each class, minimum number of properties should be specified, as unnecessary properties will make the diagram complicated. At the end of the drawing it should be understandable to the developer/coder. | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 4 | 2023-04-14 | 2023-06-09
P0007 | As a project team member, I want to design and implement UML Class Diagram to predict the design blueprint of the system during the Design phase to understand and describe attributes and operations of a class and also the constraints imposed on the system. | Technical Story Spikes | Class diagrams are static structures used to show class relationships in object-oriented programming. They are a good way to show the class structure of a system. For organizations, class diagrams help illustrate class relationships in a business application. Each class type is represented as a rectangle with three compartments for the class name, attributes, and operations. A class represents the main program unit in object-oriented programming. Classes are data structures that contain code and represent objects in an application. Using a class diagram is a good way for businesses to communicate a class structure to project stakeholders and teams. A class diagram is especially useful for communicating class hierarchies and collaborations between classes. The project team will describe each attribute that the system will have such as the ticket information (name of holder, description, category and date of issue), as well as additional characteristics such as authentication medium, users, feedback, etc. | 0 | Prority Poker - 1 (High Priority) | Planning Poker - 3 | 2023-04-14 | 2023-06-09
PB008 | As a project team member, I want to design an Entity Relationship Diagram (ERD), to provide a visual starting point for database design that can also be used to help determine the basic information system requirements. | Technical Story Spikes | An entity relationship diagram describes the interrelated components of interest in a specific domain of knowledge and composes of entity types and specifies relationships that can exist between entities. Entities refer to tables used in database designs. Attributes are regarded as properties or characteristics of entities. An ERD attribute can be denoted as a primary key, which identifies a unique attribute, or a foreign key, which can be assigned to multiple attributes. The relationships between and among those entities.With our support system, the entities that will be described and incorporated in our final solution are students, technical support agents, and additional staff members, and their attributes will be the relationship between the staff and the students to an extent that students can raise a ticket on the system, upload documents and select a specific category and the technical staff can respond to each ticket made by students and report the issue that student face, etc. | 0 | Priority Poker - 1 (High Priority) | Planning Poker - 5 | 2023-04-14 | 2023-06-09
PB009 | As a project team member, I want to develop a theme that will be implemented across the entire system during the Development phase to visualize the overall style, presentation, appearance, and atmosphere of the website. | Features | A dynamic, responsive web application will be developed across all features and extensions as they offer interactions between the server and student, i.e., the student makes a request, which the server accepts and then generates content in real time and it will be acheived through HTML (that defines the web content such as displaying hyperlinks), CSS (specifies how to display the HTML content using colors and images) and JavaScript (extends HTML and CSS functionality such as dyanmic refresh of web pages) programming languages and through the use of programming applications such as Visual Studio 2022. These applications, which often hold databases or forums and which constantly update or modify the content, usually perform updates through a content management system (CMS). Back-end programming languages to fulfill those requests on the server side. Back-end development source-code will be incorporated to design the behind-the-scene functionality to the different components. Examples are components for data storage, and code written in one or more programming languages. Students cannot access the back end. | 0 | Priority Poker - 1 (High Priority) | Planning Poker - 5 | 2023-04-14 | 2023-06-09
PB0010 | As a student, I want to be automatically logged into the system, so that I will be able to use the system. | User Story | Students, staff members and technical support technicians will be automatically logged into the system once they have entered their accurate credentials using an internal Microsoft Authorization account (Single-Sign-On authentication medium where a student will be able to view their dashboard based on their role such as a technical support technician), and will be possess persisted data and only show the student's content that is currently logged into the system. The method of incorporating unit testing is as follows: A unit test comprises of three stages: planning, where the writing of test cases and performing the unit test itself, typically using a unit testing framework like Pytest or JUnit. In the first step, developers or QA professionals prepare and review the unit test. In the next step, they write test cases and scripts. In the third step the code is tested against the authentication method of microsoft. | 1 | Priority Poker - 3 (Medium Priority) | Planning Poker - 3 | 2023-08-04 | 2023-09-08
PB0011 | As a student, I want to be able to create support tickets on the system, so that I may be able to raise any concerns that I would like assistance to. | User Story | Support ticket creation page will be displayed to the student once they have successfully logged into the system (through the sign in page) and through the inputting of their email address, the system will identify the student by stating their name, etc and will be prompted to specify and create a support ticket by stating (through the use of a creation form screen, where a student can be prompted to input their request); the name of the ticket, their category of support they would like to be assisted with, a long description provided regarding what is the query they are reqeuesting (by hovering the mouse cursor over each query type on the system), the date of ticket issued, review the status of each ticket in detail as well as they will be prompted if they would wish to upload any supporting documents to their request ticket. After a designated button is clicked to create a ticket. Students will be informed through an email that a ticket was created as well as if a ticket is escalated based on a notification that will be sent by the support personnel to a dedicated student and will be displayed above their dashboard name on the system. The student may view all their designated tickets, they created through a Create, Read, Update, Delete table situated on their dashboard. And through each ticket, an automated response will be generated by the technical personnel. As well as a Ticket length: Colour coded according to duration of ticket responses completed. Displayed on the student's dashboard will be a search bar, where they may be able to filter and search through previous tickets as guides to submit similar tickets and review responses made accordingly. | 1 | MoSCoW Model - 1 (High Priority) | Planning Poker - 2 | 2023-08-04 | 2023-09-08
PB0012 | As a technical support technician, I want to be able to prioritise the tickets on the system, so that it may be responded to based on the severity of the ticket. | Features | Technical support staff can prioritize tickets requested by students and each ticket will be displayed on the technical support dashboard and technical staff will be given the authority to sort each ticket in a given grid based on the extremity (ranging from high, medium and low priority on the system) and may respond to each accordingly. | 1 | Opportunity Scoring - 3 (Medium Priority) | Three-Point Method - 3 | 2023-08-04 | 2023-09-08
PB0013 | As a student, I want to be able to cancel and delete a ticket request from the system, so that I may be able to resend a new ticket in the case I encountered an error with the original ticket. | User Story | Students can remove a ticket request from the system and unsend a ticket as a possible error and it will be viewed on dashboard of the technical support technician as a retractable ticket entry and the support technican will be notified through an email response indicating that a ticket was cancelled by a student and the email must appear on the support dashboard and no further assistance must be provided by the technican to respond to that specified ticket. | 1 | Stack Ranking - 3 (Medium Priority) | Dot Voting - 5 | 2023-08-04 | 2023-09-08
PB0014 | As the system, I want to notify technical support technicians through an email that a certain ticket(s) have not been responded to within 5 working days. | Features | The system must view all tickets created and if certain tickets did not have any responses within 5 working days must be investigated into, as well as a Ticket: 5 day email reminder will be sent out to staff members to respond to student request queries, so that technical staff may be able to respond to that ticket during the next business times and if neccessary, escalate that specific query to upper management for additional assistance. A possible coding solution to implement an appointment class, where C# MVC model class inherits the data class that specifies the date, time, name of student that the ticket was made and subtract the current time from the creation time of the ticket, so that a technical support staff member will be notified once they log into the system at the next conveinent time. | 2 | MoSCoW Model - 1 (High Priority) | Planning Poker - 2 | 2023-09-09 | 2023-10-20
PB0015 | As a technical staff member and manager, I want to be able to create a list of templates for automatic responses to support queries. | Features | Staff and managers can create templates to respond to student requests quickly and efficiently and adjust my response according to the student's query so that I may respond to additional, and more complex queries. | 2 | Priority Poker - 1 (High Priority) | Planning Poker - 1 | 2023-09-09 | 2023-10-20
PB0016 | As a technical support technican, I want to be able to view and use various response templates to effectively reply to requests. | User Story | Technical staff members can view and use the established automated responses they created on their dashboard to effectively and efficiently reply to recurring queries | 2 | Stack Ranking - 1 (Medium Priority) | Bucket System - 1 | 2023-09-09 | 2023-10-20
PB0017 | As a technical support technican, I want to be able to respond to support queries requested by students without templates and close responded tickets to provide assistance to technical issues. | User Story | Technical support technicians must be able to respond direclty to each user-requested support ticket query irregardless of using generated templates to provide a quick automated response but to also give precise instruction and guidance to each student in how they can resolve their current issue and to prevent similar issues in the future. | 2 | Opportunity Scoring - 1 (High Priority) | Planning Poker - 1 | 2023-09-09 | 2023-10-20
PB0018 | As a student, I want to be able to contact the additional support agent if my ticket is still unresolved. | User Story | Additional support technicians is available for contacting with regards to extra assistance, if student requested emails that will be converted to support tickets, should be escalated. | 2 | Opportunity Scoring - 1 (Medium Priority) | Relative Sizing - 2 | 2023-09-09 | 2023-10-20
PB0019 | As a student, I want to be able to provide feedback and rate the use of the overall system through a star selection method and by stating possible improvements required for future assistance provided by staff members. | Features | Rating system for students and technical staff, so that they may provide direct responses to opertating the system in relation to the technical support team when creating the system through the use of selecting a five star range category options and the student's will be prompted to answer questions based on their experience in using the system such as How would you rate the support you received? (1–5 scale) If 1–3: How could we improve? If 4-–5: What did you love about the experience? What’s the main reason for your score? What should we do to WOW you? (optional) Software developers must allow students to customize their responses on the system in terms of record keeping to ensure that the questions are relevant for future use such as flexibility. | 2 | Opportunity Scoring - 1 (Medium Priority) | Three-Point Method - 3 | 2023-09-09 | 2023-10-20
PB0020 | As a software developer, I want to be able to construct a report to individually log each request made by a specific student and staff member. | User Story | Technical staff should produce reports of all tickets requested by each student and that each staff member assists with, so that they may be able to keep a digital record-base filing scheme, where all ticket requests and responses are orgainized in a systematic manner and is easy to reference other ticket requests. | 2 | Priortiy Poker - 1 (High Priority) | T-Shirt Sizes - 4 | 2023-09-09 | 2023-10-20

## Sprint Backlog
Story ID | Sprint Goals | User Story | Sprint No. | Tasks | Priority | Acceptance Criteria | Assignee | Status | Dependencies
SB001 | Research and Design Thinking | As a project team member, I want to conduct online research to investigate authentication and signing in to the website during the Sprint Planning process. | 0 | Team members conduct user research, share tasks and implement design thinking principles, for web development and share during meetings. | High | Team members should research and be aware of two-factor verification for students, prompt for a second verification method and issuing a sign-in without requiring a password, using your username and your mobile device with your fingerprint, face, or PIN. | Team Members | Completed | None
SB002 | Sprint Planning Meetings | As a project team member, I want to create a prioritized Product Backlog with a list of features and user stories during the Sprint Planning Meeting so that we can plan and prioritize our work effectively and proceed with responding to user stories from the product backlog. | 0 | Team members meet every Tuesday and Friday to talk about the progress of their work. | High | A project schedule with relevant deliverables to be created, so team members should be aligned on what needs to be accomplished. | Team Members | In Progress | None
SB003 | User Research for Requirement Analysis | As a project team member, I want to conduct user research and gather requirements during the Requirement Analysis phase so that we have a clear understanding of the users' needs and expectations | 0 | Conduct user research for Requirement Analysis phase via user case studies, surveys and interviews, as these would give the team and stakeholders a thorough understanding of the different user types and needs. | High | A document containing brainstorming various scenarios - supervised by the Project Manager. | Cameron + Mishra | Completed | SB001
SB004 | User Personas | As a project team member, I want to create user personas and user stories during the Requirement Analysis phase to better understand our target audience and their specific requirements. | 0 | Creation of user personas from user research findings. | High | Relevant user personas created, to enhance target audience requirements. | Cameron | Completed | SB003
SB005 | UX/UI Design | As a project team member, I want to develop a UI/UX design that meets user requirements during the Design phase to ensure an intuitive and user-friendly website will be implemented. | 0 | Create an efficient UX/UI layout and well-thought-out system of transitions, that is compatible with users (user-friendly) | High | UX/UI Design/ mockups should provide the basic concept of system and accurately depict how user-friendly the system is. | Philani + Mishra | To Do | SB004
SB006 | UML Use Case Diagram | As a project team member, I want to create a UML Use Case Diagram to visualize the system's functionality during the Design phase so that we have a clear understanding of how different components interact with each other. | 0 | Create a UML Use Case Diagram that efficently depicts the system's functionality and operations. | High | The name (such as Technical Support System) should be meaningful to describe the aspect of the system. Each element and their relationships should be identified in advance. The Responsibility (attributes and methods) of each class should be clearly identified. For each class, minimum number of properties should be specified, as unnecessary properties will make the diagram complicated. At the end of the drawing it should be understandable to the developer/coder. | Candice + Akhona | Completed | None
SB007 | UML Class Diagram | As a project team member, I want to design and implement UML Class Diagrams to predict the design blueprint of the system during the Design phase to understand and describe attributes and operations of a class and also the constraints imposed on the system. | 0 | Design UML Class Diagrams the system's design/blueprint, so team members can understand operations and constraints imposed. | High | The project team will describe each attribute that the system will have such as the ticket information (name of holder, description, category and date of issue), as well as additional characteristics such as authentication medium, users, feedback, etc. | Candice + Akhona | Completed | None
SB008 | ERD Diagram | As a project team member, I want to design an Entity Relationship Diagram (ERD), to provide a visual starting point for database design that can also be used to help determine the basic information system requirements. | 0 | Design ERD diagram that shows relationship between the staff and the students to an extent that students can raise a ticket on the system, upload documents and select a specific category and the technical staff can respond to each ticket made by students and report the issue that student face, etc. | High | Members need to outline the relationship between the staff, students and system, so implementation is clear and manageable. | Candice + Akhona | Completed | None
SB009 | Project Theme | As a project team member, I want to develop a theme that will be implemented across the entire system during the Development phase to visualize the overall style, presentation, appearance, and atmosphere of the website. | 0 | Decide and implement project theme for Design and Development phase. | High | Team members need to agree upon a theme for system, such as responsive web layout. Backend code should not be accessed by students. HTML, CSS and JavaScript to be used as these applications perform updates through CMS (content management ystsem). | Team Members | Progress | None
SB010 | Support Tickets Creation | As a student, I want to be able to create support tickets on the system, so that I may be able to raise any concerns that I would like assistance to. | 1 | Create ticket support screen for users to enter the details, their problem and ticket priority level. Thereafter, when submitted, user should receive an automated response informing them about their ticket submission. | High | The system will identify the student by stating their name, etc and will be prompted to specify and create a support ticket by stating (through the use of a creation form screen, where a student can be prompted to input their request); the name of the ticket, their category of support they would like to be assisted with, a long description provided regarding what is the query they are reqeuesting (by hovering the mouse cursor over each query type on the system), the date of ticket issued, review the status of each ticket in detail as well as they will be prompted if they would wish to upload any supporting documents to their request ticket. After a designated button is clicked to create a ticket, the student may view all their designated tickets, they created through a Create, Read, Update, Delete table situated on their dashboard. And through each ticket, an automated response will be generated by the technical personnel. | Team Members | To Do | None
SB011 | Login | As a student, I want to be automatically logged into the system, so that I will be able to use the system | 1 | Enable users to be automatically logged in, after they have entered their accurate credentials using an internal Microsoft Authorization account (Single-Sign-On authentication medium. In the first step, developers or QA professionals prepare and review the unit test. In the next step, they write test cases and scripts. In the third step the code is tested against the authentication method of microsoft. | Medium | Students, staff members and technical support technicians will be automatically logged into the system once they have entered their accurate credentials using an internal Microsoft Authorization account (Single-Sign-On authentication medium where a student will be able to view their dashboard based on their role such as a technical support technician), and will be possess persisted data and only show the student's content that is currently logged into the system. In the first step, developers or QA professionals prepare and review the unit test. In the next step, they write test cases and scripts. In the third step the code is tested against the authentication method of microsoft. | Team Members | To Do | None
SB012 | Tickets Prioritization | As a technical support technician, I want to be able to prioritise the tickets on the system, so that it may be responded to based on the severity of the ticket. | 1 | Implement front-end and backend code for tickets submitted to be displayed on dashboard, where technical support team should be able to prioritize tickets. | Medium | Technical support staff can prioritize tickets requested by students and each ticket will be displayed on the technical support dashboard and technical staff will be given the authority to sort each ticket in a given grid based on the extremity (ranging from high, medium and low priority on the system) and may respond to each accordingly. | Team Members | To Do | None
SB013 | Retractable Ticket | As a student, I want to be able allowed to cancel, retract and delete a ticket request from the system, so that I may be able to resend a new ticket in the case I encountered an error with the original ticket | 1 | Enable feature that allows a ticket to be removed or unsend the ticket and depict as 'retractable ticket entry' on technical support dashbaord. | Medium | Students can remove a ticket request from the system and unsend a ticket as a possible error and it will be viewed on dashboard og the technical support technician as a retractable ticket entry. | Developer 1 | To Do | SB012
SB014 | Notifications | As a student, I want to be able to receive a notification via email or message that a staff member has acknowledged a support query has been created. | 2 | Create automated response and implement it in functionality that would send the response to the relevant user. | Medium | Informing the student through an email that a ticket was created as well as if a ticket is escalated based on a notification that will be sent by the support personnel to a dedicated student and will be displayed above their dashboard name on the system. | Developer 1 | To Do | None
SB015 | Unattended Ticket Notification | As a technical support technician, I want to be able to issue a notification that a certain ticket(s) have not been responded to within 5 working days. | 2 | Create a template response that a support technician can edit and be able to send to staff members, when a ticket has not been solved within 5 working days. A possible coding solution to implement an appointment class, where C# MVC model class inherits the data class that specifies the date, time, name of student that the ticket was made and subtract the current time from the creation time of the ticket, so that a technical support staff member will be notified once they log into the system at the next conveinent time. | High | Ticket: 5 day reminder to staff members to respond to student request queries, so that technical staff may be able to respond to that ticket during the next business times and if neccessary, escalate that specific query to upper management for additional assistance. | Developer 2 | To Do | SB012
SB016 | Unattended Ticket Notification | As a technical support technician, I want to be able to issue a notification that a certain ticket(s) have not been responded to within 7 days or longer. | 2 | Create a template response that a support technician can edit and be able to send to staff members, when a ticket has not been solved within 7 working days. A possible coding solution to implement an appointment class, where C# MVC model class inherits the data class that specifies the date, time, name of student that the ticket was made and subtract the current time from the creation time of the ticket, so that a technical support staff member will be notified once they log into the system at the next conveinent time. | High | Ticket: 48 hour reminder to staff members to respond to student request queries, so that technical staff may be able to respond to that ticket during the next business times and if neccessary, escalate that specific query to upper management for additional assistance. | Developer 2 | To Do | SB014
SB017 | Response Templates | As a technical support staff, I want to be able to view various response templates to effectively reply to requests. | 2 | Create response templates for staff members for quick and effective responses. Implement backend code that enables the template to be sent to user that submitted the ticket. | Medium | Staff can create templates to respond to student requests quickly and efficiently and adjust my response according to the student's query so that I may respond to additional, and more complex queries. | Developer 3 | To Do | None
SB018 | Additional Technical Support | As a student, I want to be able to contact the additional support agent if my ticket is still unresolved. | 2 | Design and code feature that allows student to escalate unresolved ticket, by contacting a support agent (through email). | Medium | Additional support technicians are available for contacting with regards to extra assistance, if student requested emails that will be converted to support tickets, should be escalated. | Developer 3 | To Do | None
SB019 | Feedback System | As a student, I want to be able to provide feedback and rate the use of the overall system through a star selection method and by stating possible improvements required for future assistance provided by staff members | 2 | Code function that allow students to customize their responses on the system in terms of record keeping to ensure that the questions are relevant for future use such as flexibility. Implement front-end design, if needed. | Medium | Rating system for students and technical staff, so that they may provide direct responses to operating the system in relation to the technical support team, when creating the system through the use of selecting a five star range category options and the student's will be prompted to answer questions based on their experience in using the system, such as; How would you rate the support you received? (1–5 scale) If 1–3: How could we improve? If 4-–5: What did you love about the experience? What’s the main reason for your score? What should we do to WOW you? (optional) | Developer 4 | To Do | None
SB020 | Log Reports | As technical support, I want to be able to construct a log report to individually log each request made by a specific student. | 2 | Implement log report functionality, through code, so technical support can log requests by specific students. | High | Technical staff should produce log reports of all tickets requested by each student and that each staff member assists with, so that they may be able to keep a digital record-base filing scheme, where all ticket requests and responses are orgainized in a systematic manner and is easy to reference other ticket requests. | Developer 4 | To Do | None

## Burndown Chart
SPRINT 0 BURNDOWN CHART
Backlog Task and ID |  | Hours Planned | Assigned To | Start Date | End Date | Status
User Story #1
Team members conduct user research, share tasks and implement design thinking principles, for web development and share during meetings. |  | 6 | Team Members | 2023-04-28 | 2023-05-03 | Completed
User Story #2
Team members meet every Tuesday and Friday to talk about the progress of their work. |  | 1 per meeting | Team Members | 2023-04-28 |  | Ongoing
User Story #3
Conduct user research for Requirement Analysis phase via user case studies, surveys and interviews, as these would give the team and stakeholders a thorough understanding of the different user types and needs. |  | 20 | Cameron and Mishra | 2023-05-04 | 2023-05-17 | Completed
User Story #4
Creation of user personas from user research findings. |  | 3 | Cameron and Mishra |  |  | To Do
User Story #5
Create an efficient UX/UI layout and well-thought-out system of transitions, that is compatible with users (user-friendly) |  | 15 | Philani and Mishra |  |  | In Progress
User Story #6
Create a UML Use Case Diagram that efficently depicts the system's functionality and operations. |  | 8 | Candice and Akhona | 2023-05-30 | 2023-06-10 | Completed
User Story #7
Design UML Class Diagrams the system's design/blueprint, so team members can understand operations and constraints imposed. |  | 9 | Candice and Akhona | 2023-06-11 |  | In Progress
User Story #8
Decide and implement project theme for Design and Development phase. |  |  | Team Members |  |  | In Progress
User Story #9
Enable users to be automatically log in, after they have entered their accurate credentials using an internal Microsoft Authorization account (Single-Sign-On authentication medium. In the first step, developers or QA professionals prepare and review the unit test. In the next step, they write test cases and scripts. In the third step the code is tested against the authentication method of microsoft. |  | 17 | Daylin | 2023-07-17 |  | In Progress
User Story #10
Create ticket support screen for users to enter the details, their problem and ticket priority level. Thereafter, when submitted, user should receive an automated response informing them about their ticket submission. |  | 24 | Philani | 2023-07-21 |  | In Progress
User Story #11
Implement front-end and backend code for tickets submitted to be displayed on dashboard, where technical support team should be able to prioritize tickets. |  | 26 | Jordan + Cameron + Philani |  |  | To Do
User Story #12
Create automated response and implement it in functionality that would send the response to the relevant user. |  | 4 | Daylin + Akhona |  |  | To Do
User Story #13
Enable feature that allows a ticket to be removed or unsend the ticket and depict as 'retractable ticket entry' on technical support dashbaord. |  | 4 | Mishra + Candice |  |  | To Do
User Story #14
Create a template response that a support technician can edit and be able to send to staff members, when a ticket has not been solved within 5 working days. |  | 3 | Mishra |  |  | To Do
User Story #15
Create a template response that a support technician can edit and be able to send to staff members, when a ticket has not been solved within 7 working days. |  | 3 | Cameron |  |  | To Do
User Story #16
Create response templates for staff members for quick and effective responses. Implement backend code that enables the template to be sent to user that submitted the ticket. |  | 3 | Candice |  |  | To Do
User Story #17
Design and code feature that allows student to escalate unresolved ticket, by contacting a support agent (through email). |  | 15 | Mishra + Cameron |  |  | To Do
User Story #18
Code function that allow students to customize their responses on the system in terms of record keeping to ensure that the questions are relevant for future use such as flexibility. Implement front-end design, if needed. |  | 15 | Philani + Daylin |  |  | To Do
User Story #19
Implement log report functionality, through code, so technical support can log requests by specific students. |  | 10 | Jordan + Candice |  |  | To Do
User Story #20
Generate common questions and answers users may have, display it through front-end FAQ page and enable staff members to access it for common queries. |  | 5 | Team Members | 2023-07-21 |  | In Progress
| TOTAL HOURS = | 190